## Project schedule
| CIVE 202 Project #5 | Project Members |  |  |  |  | Project start: | [7 empty] | 2026-02-25 | [9 empty] | Project end: | [7 empty] | 2026-05-08
| GEST-01-C Automation of Steel Beam Calculations (Steel Design) | Jacob Oetken, Tyler Thiede, Michael McCarthy, Bryce Ripley |  |  |  |  | Display week: | [7 empty] | 1
SIMPLE GANTT CHART by Vertex42.com
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html | [5 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13 | [6 empty] | 2026-04-20 | [6 empty] | 2026-04-27 | [6 empty] | 2026-05-04
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2026-02-23 to 2026-05-10
 | time axis 2026-02-23 to 2026-05-10
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Planning for function development
| Project Schedule Planning (Gantt Chart) | Mac | 100% | 2026-03-04 | 2026-03-04 | 1
| TASK 1: AISC Procedural Review | All Members | 100% | 2026-03-05 | 2026-03-08
| TASKS 2-4: Flow Chart | All Members | 100% | 2026-03-09 | 2026-03-12
| TASK 5: Scenario Definition Planning | All Members | 100% | 2026-03-13 | 2026-03-18
Draft functions in Python
| TASK 2: Python Function Creation | All Members | 100% | 2026-03-13 | 2026-03-23 | 11
| TASK 3: User Input Flow | All Members | 100% | 2026-03-24 | 2026-03-29 | 6
| TASK 4: Output Formatting | All Members | 100% | 2026-03-30 | 2026-04-04 | 6
| TASK 5: Scenario Definition and Validation | All Members | 100% | 2026-04-05 | 2026-04-09
| TASK 6: Graphing and Visuals | All Members | 0% | 2026-04-10 | 2026-04-14
Execution
| Data cleaning and Processing | All Members | 100% | 2026-04-15 | 2026-04-16
| Testing and validation | All Members | 80% | 2026-04-17 | 2026-04-18
| Technical Executive Summary | All Members | 0% | 2026-04-19 | 2026-04-22
| Non-technical Executive Summary | All Members | 0% | 2026-04-23 | 2026-04-26
| Annotated Code Document (ACD) | Jacob Oetken | 0% | 2026-03-13 | 2026-04-14
| Scope of Work (SOW) | Jacob | 100% | 2026-02-25 | 2026-02-26
| README document | Jacob and Mac | 0% | 2026-04-19 | 2026-04-20
| GitHub Repository Creation | Tyler | 100% | 2026-02-25 | 2026-02-26
| Final Project integration and submission | All Members | 50% | 2026-05-06 | 2026-05-08
Evaluation
| Monitor progress | All Members | 70% | 2026-02-25 | 2026-05-07 | 72
| Track Billable Hours | All Members | 15% | 2026-02-25 | 2026-05-07
| Evaluate progress | All Members | 0% | 2026-03-13 | 2026-05-07 | 56
| Gather feedback | All Members | 0% | 2026-05-08 | 2026-05-09 | 2