## Week Ending 2.28
Week Ending | 2026-02-28
Day of Week | Date | Person | Hours Worked | Tasks completed | Hourly Rate | Total Compensation
Monday | 2026-02-23 | Tyler | 1 | Added deliverables and project tasks section to SOW | 21.5 | 21.5
Tuesday | 2026-02-24 | Jacob | 1.5 | Format SOW, input roles and responsibilities | 22.5 | 33.75
Wednesday | 2026-02-25 | Michael | 1 | Review and finalize goals and objectives of SOW | 21.5 | 21.5
Thursday | 2026-02-26 | Jacob | 0.2 | Submit SOW | 22.5 | 4.5
Friday | 2026-02-27 | Jacob | 0.4 | Create Timesheet Template | 22.5 | 9
Total |  |  | 4.1 | Total |  | 90.25
| Individual Totals for the Week | Cost
| Tyler | 21.5
| Jacob | 47.25
| Michael | 21.5
| TOTAL COST | 90.25
Formulas:
Date = [Date, row above]+1

## Week Ending 3.7
Week Ending | 2026-03-07
Day of Week | Date | Person | Hours Worked | Tasks completed | Hourly Rate | Total Compensation
Monday | 2026-03-02 | Jacob | 0 |  | 22.5 | 0
Tuesday | 2026-03-03 | Michael | 0 |  | 21.5 | 0
Wednesday | 2026-03-04 | Tyler | 0 |  | 21.5 | 0
Thursday | 2026-03-05 | Jacob | 0 |  | 22.5 | 0
Friday | 2026-03-06 | Jacob | 0.5 | Flow Chart Discussion | 22.5 | 11.25
Friday | 2026-03-06 | Tyler | 0.5 | Flow Chart Discussion | 21.5 | 10.75
Friday | 2026-03-06 | Michael | 0.5 | Flow Chart Discussion | 21.5 | 10.75
Total |  |  | 1.5 | Total |  | 32.75
| Individual Totals for the Week | Cost
| Tyler | 10.75
| Jacob | 11.25
| Michael | 10.75
| TOTAL COST | 32.75
Formulas:
Date = [Date, row above]+1
Date = [Date, row below]

## Week Ending 3.14
Week Ending | 2026-03-14
Day of Week | Date | Person | Hours Worked | Tasks completed | Hourly Rate | Total Compensation
Monday | 2026-03-09 | Jacob | 0 |  | 22.5 | 0
Tuesday | 2026-03-10 | Michael | 0 |  | 21.5 | 0
Wednesday | 2026-03-11 | Jacob | 1.5 | Complete and submit flow diagram | 22.5 | 33.75
Wednesday | 2026-03-11 | Tyler | 1.5 | Complete and submit flow diagram | 21.5 | 32.25
Thursday | 2026-03-12 | Tyler | 0 |  | 21.5 | 0
Friday | 2026-03-13 | Michael | 0 |  | 21.5 | 0
Total |  |  | 3 | Total |  | 66
| Individual Totals for the Week | Cost
| Tyler | 32.25
| Jacob | 33.75
| Michael | 0
| TOTAL COST | 66
Formulas:
Date = [Date, row above]+1
Date = [Date, row above]

## Week Ending 3.21
Week Ending | 2026-03-21
Day of Week | Date | Person | Hours Worked | Tasks completed | Hourly Rate | Total Compensation
Monday | 2026-03-16 | Jacob | 0 |  | 22.5 | 0
Tuesday | 2026-03-17 | Michael | 0 |  | 21.5 | 0
Wednesday | 2026-03-18 | Tyler | 0 |  | 21.5 | 0
Wednesday | 2026-03-18 | Jacob | 0 |  | 22.5 | 0
Thursday | 2026-03-19 | Michael | 0 |  | 21.5 | 0
Friday | 2026-03-20 | Tyler | 0 |  | 21.5 | 0
Total |  |  | 0 | Total |  | 0
| Individual Totals for the Week | Cost
| Tyler | 0
| Jacob | 0
| Michael | 0
| Bryce | 0
| TOTAL COST | 0
Formulas:
Date = [Date, row above]+1
Date = [Date, row above]

## Week Ending 3.28
Week Ending | 2026-03-28
Day of Week | Date | Person | Hours Worked | Tasks completed | Hourly Rate | Total Compensation
Monday | 2026-03-23 | Jacob | 0 |  | 22.5 | 0
Tuesday | 2026-03-24 | Michael | 0 |  | 21.5 | 0
Wednesday | 2026-03-25 | Tyler | 1 | Work on creating reproducable methods | 21.5 | 21.5
Wednesday | 2026-03-25 | Michael | 1 | Work on creating reproducable methods | 21.5 | 21.5
Thursday | 2026-03-26 | Jacob | 1 | Work on creating reproducable methods | 22.5 | 22.5
Friday | 2026-03-27 | Jacob | 1.5 | Start writing up the initial code | 22.5 | 33.75
Total |  |  | 4.5 | Total |  | 99.25
| Individual Totals for the Week | Cost
| Tyler | 21.5
| Jacob | 56.25
| Michael | 21.5
| Bryce | 0
| TOTAL COST | 99.25
Formulas:
Date = [Date, row above]+1
Date = [Date, row above]

## Week Ending 4.4
Week Ending | 2026-04-04
Day of Week | Date | Person | Hours Worked | Tasks completed | Hourly Rate | Total Compensation
Monday | 2026-03-30 | Michael | 0 |  | 21.5 | 0
Tuesday | 2026-03-31 | Tyler | 0 |  | 21.5 | 0
Wednesday | 2026-04-01 | Jacob | 1.5 | Continue working on code for initial results | 22.5 | 33.75
Wednesday | 2026-04-01 | Tyler | 1.5 | Continue working on code for initial results | 21.5 | 32.25
Thursday | 2026-04-02 | Michael | 0.8 | Review initial results | 21.5 | 17.2
Friday | 2026-04-03 | Tyler | 0 |  | 21.5 | 0
Total |  |  | 3.8 | Total |  | 83.2
| Individual Totals for the Week | Cost
| Tyler | 32.25
| Jacob | 33.75
| Michael | 17.2
| Bryce | 0
| TOTAL COST | 83.2
Formulas:
Date = [Date, row above]+1
Date = [Date, row above]

## Week Ending 4.11
Week Ending | 2026-04-11
Day of Week | Date | Person | Hours Worked | Tasks completed | Hourly Rate | Total Compensation
Monday | 2026-04-06 | Tyler | 0 |  | 21.5 | 0
Tuesday | 2026-04-07 | Jacob | 0 |  | 22.5 | 0
Wednesday | 2026-04-08 | Michael | 0 |  | 21.5 | 0
Thursday | 2026-04-09 | Tyler | 0 |  | 21.5 | 0
Friday | 2026-04-10 | Tyler | 0.7 | Review/TA checkin | 21.5 | 15.05
Friday | 2026-04-10 | Jacob | 0.7 | Review/TA checkin | 22.5 | 15.75
Friday | 2026-04-10 | Michael | 0.7 | Review/TA checkin | 21.5 | 15.05
Total |  |  | 2.1 | Total |  | 45.85
| Individual Totals for the Week | Cost
| Tyler | 15.05
| Jacob | 15.75
| Michael | 15.05
| Bryce | 0
| TOTAL COST | 45.85
Formulas:
Date = [Date, row above]+1

## Week Ending 4.18
Week Ending | 2026-04-18
Day of Week | Date | Person | Hours Worked | Tasks completed | Hourly Rate | Total Compensation
Monday | 2026-04-13 | Tyler | 0 |  | 21.5 | 0
Tuesday | 2026-04-14 | Michael | 0 |  | 21.5 | 0
Wednesday | 2026-04-15 | Bryce | 2 | Review code, and other files to catch up to speed with the progress | 21.5 | 43
Wednesday | 2026-04-15 | Bryce | 0 |  | 21.5 | 0
Thursday | 2026-04-16 | Jacob | 0.5 | Compile files for peer review | 22.5 | 11.25
Friday | 2026-04-17 | Tyler | 0 |  | 21.5 | 0
Total |  |  | 2.5 | Total |  | 54.25
| Individual Totals for the Week | Cost
| Tyler | 0
| Jacob | 11.25
| Michael | 0
| Bryce | 43
| TOTAL COST | 11.25
Formulas:
Date = [Date, row above]+1
Date = [Date, row above]

## Week Ending 4.25
Week Ending | 2026-04-25
Day of Week | Date | Person | Hours Worked | Tasks completed | Hourly Rate | Total Compensation
Monday | 2026-04-20 | Jacob | 0 |  | 22.5 | 0
Tuesday | 2026-04-21 | Tyler | 0 |  | 21.5 | 0
Wednesday | 2026-04-22 | Bryce | 0 |  | 21.5 | 0
Wednesday | 2026-04-22 | Michael | 0 |  | 21.5 | 0
Thursday | 2026-04-23 | Tyler | 0 |  | 21.5 | 0
Friday | 2026-04-24 | Jacob | 2 | Lab Work time | 22.5 | 45
Friday | 2026-04-24 | Tyler | 2 | Lab Work time | 21.5 | 43
Friday | 2026-04-24 | Bryce | 2 | Lab Work time | 21.5 | 43
Friday | 2026-04-24 | Michael | 2 | Lab Work time | 21.5 | 43
Total |  |  | 2 | Total |  | 45
| Individual Totals for the Week | Cost
| Tyler | 43
| Jacob | 45
| Michael | 43
| Bryce | 43
| TOTAL COST | 131
Formulas:
Date = [Date, row above]+1
Date = [Date, row above]

## Week Ending 5.2
Week Ending | 2026-05-02
Day of Week | Date | Person | Hours Worked | Tasks completed | Hourly Rate | Total Compensation
Monday | 2026-04-27 | Tyler | 0 |  | 21.5 | 0
Tuesday | 2026-04-28 | Michael | 0 |  | 21.5 | 0
Wednesday | 2026-04-29 | Bryce | 0 |  | 21.5 | 0
Wednesday | 2026-04-29 | Bryce | 0 |  | 21.5 | 0
Thursday | 2026-04-30 | Jacob | 0 |  | 22.5 | 0
Friday | 2026-05-01 | Tyler | 0 |  | 21.5 | 0
Total |  |  | 0 | Total |  | 0
| Individual Totals for the Week | Cost
| Tyler | 0
| Jacob | 0
| Michael | 0
| Bryce | 0
| TOTAL COST | 0
Formulas:
Date = [Date, row above]+1
Date = [Date, row above]

## Week Ending 5.9
Week Ending | 2026-05-09
Day of Week | Date | Person | Hours Worked | Tasks completed | Hourly Rate | Total Compensation
Monday | 2026-05-04 | Tyler | 0 |  | 21.5 | 0
Tuesday | 2026-05-05 | Michael | 0 |  | 21.5 | 0
Wednesday | 2026-05-06 | Jacob | 0 |  | 22.5 | 0
Wednesday | 2026-05-06 | Bryce | 0 |  | 21.5 | 0
Thursday | 2026-05-07 | Tyler | 2 | Create, and draft the formal report | 21.5 | 43
Thursday | 2026-05-07 | Bryce | 2 | Create, and draft the formal report | 21.5 | 43
Thursday | 2026-05-08 | Jacob | 2 | Annotated Code document, update required documents | 22.5 | 45
Thursday | 2026-05-08 | Michael | 2 | Finishing touches on the code portion | 21.5 | 43
Friday | 2026-05-06 | Tyler | 3 | Create both technical and non-technical executive summaries, as well as final touches for the project | 21.5 | 64.5
Friday | 2026-05-07 | Bryce | 3 | Create both technical and non-technical executive summaries, as well as final touches for the project | 21.5 | 64.5
Friday | 2026-05-07 | Jacob | 3 | Create both technical and non-technical executive summaries, as well as final touches for the project | 22.5 | 67.5
Friday | 2026-05-08 | Michael | 3 | Create both technical and non-technical executive summaries, as well as final touches for the project | 21.5 | 64.5
Total |  |  | 20 | Total |  | 435
| Individual Totals for the Week | Cost
| Tyler | 107.5
| Jacob | 112.5
| Michael | 107.5
| Bryce | 107.5
| TOTAL COST | 327.5
Formulas:
Date = [Date, row above]+1
Date = [Date, row above]

## Summary
Person | Personal Compensation
Tyler | 283.8
Jacob | 366.75
Michael | 236.5
Bryce | 193.5
| Total Hours Worked | Total Compensation
| 43.5 | 1080.55